## Risk Register
PROJECT RISK REGISTER
PROJECT NAME |  | Flight Bite Knights Risk Register
COMPANY NAME |  | Flight Bite Knights
PROJECT MANAGER |  | J. Fluker | [6 empty] | DATE | 2025-07-08
Risk ID | Date | Risk Name / Impact Description | Risk Category | Likelihood of Occurrence | Risk Impact | Risk Priority | Risk Owner | Mitigation Plan | Status | Comments
1 | 2025-07-08 | Drone malfunction or crash which could lead to property damage, injury, food loss, legal liability, reputational damage. | Operations | Unlikely | Medium | 2 (Medium) | Project Manager | Perform routine maintenance and pre-flight diagnostics. Use redundant systems (fail-safes, emergency landings.) Avoid high-risk areas with geofencing. | In Progress
2 | 2025-07-08 | Theft or physical tampering could lead to lost inventory, data breach (if onboard systems store info), customer distrust. | Security | Unlikely | High | 3 (High) | Project Manager | Use tamper-proof casings and GPS-based live tracking. Limit landing to secure and verified delivery zones. Equip drones with cameras and sirens to deter theft. Rapid geofencing lock-down if drone goes off-course. | In Progress
3 | 2025-07-08 | Regulatory non-compliance could lead to legal penalties, grounded operations, reputational risk. | Legal | Unlikely | High | 3 (High) | Project Manager | Work closely with aviation authorities (e.g., FAA, EASA). Utilize real-time compliance monitoring | In Progress
4 | 2025-07-08 | Environmental hazards could lead to drone damage and public safety risks. | Environmental | Likely | Medium | 1 (Low) | Project Manager | Build drones with rugged, weather-resistant materials. Include LiDAR/obstacle detection. Use AI powered weather and flight path prediction. | In Progress
5 | 2025-07-08 | Drone Hijacking (GPS Spoofing / Signal Jamming) could lead to loss of control, crashes, thieves rerouting to steal goods, and data breaches. | Security | Unlikely | High | 3 (High) | Project Manager | Use encrypted control signals and anti-jamming tech. Integrate inertial navigation systems (INS) | In Progress
6 | 2025-07-08 | Customer data breaches could result in legal/regulatory fines, customer trust loss, lawsuits. | Security | Unlikely | High | 3 (High) | Project Manager | Use end-to-end encryption of customer and delivery data. Role-based access control and regular audits. Use secure authentication protocols (OAuth2, MFA). | In Progress
7 | 2025-07-08 | Mobile app or backend exploits could lead to disruption of service, impersonation, price manipulation. | Security | Unlikely | High | 3 (High) | Project Manager | Conduct regular penetration testing and code reviews. Secure DevOps (DevSecOps) practices. Use API gateway with rate limiting and threat detection. | In Progress
8 | 2025-07-08 | Cloud or Platform Downtime (Denial of Service) could result in delivery delays, order loss, and revenue loss. | Security | Unlikely | High | 3 (High) | Project Manager | Use CDN and DDoS protection (e.g., Cloudflare, AWS Shield). Multi-cloud redundancy and offline flight modes. Build in failover paths and queuing systems. | In Progress